## Sheet1
Stakeholder Name/Group | Role in Project | Power / Influence | Interest Level | Quadrant (Mendelow’s) | Key Motivations / Requirements | Potential Blockers / Risks | Communication Strategy
Business Sponsor / CEO | Project Sponsor; provides funding and strategic direction. | High | Medium | Keep Satisfied | ROI, overall cost reduction in penalties, and brand reputation (compliant fleet). | Sudden budget shifts or changing business priorities. | Monthly High-level Progress Reports & Quarterly Steering Committee Meetings.
Fleet Manager | Primary End-User; manages the daily operations and vehicle health. | High | High | Manage Closely | Ease of use, real-time alerts, and accurate tracking of all vehicle docs (RC, Insurance, PUC). | Resistance to moving away from manual/legacy Excel systems. | Weekly Status Meetings & Dedicated WhatsApp Group for feedback.
Lead Developer / IT Team | Technical Execution; building the logic, database, and UI. | Medium | High | Manage Closely | Clear technical requirements, stable APIs (Mock Vahan), and clean code architecture. | Technical debt, integration issues with external data sources. | Daily Stand-ups & Real-time collaboration via Slack/Cursor.
RTO Compliance Consultant | External Expert; ensures the system follows latest Indian transport laws. | Medium | Medium | Keep Satisfied | Correct interpretation of RTO rules, fine structures, and document validity periods. | Regulatory changes (e.g., new Bharat Stage norms) not updated in app. | Bi-Weekly Check-ins via Email or Video Call.
Finance / Accounts Dept. | Monitors operational costs and processes insurance/permit payments. | Medium | High | Keep Informed | Precise reporting on "Cost of Compliance" and avoiding "unplanned expenses" (fines). | Delay in approving funds for document renewals despite alerts. | Monthly Financial Impact Reports via Email.
Fleet Drivers / Operations Staff | Data contributors; update service logs and provide on-ground status. | Low | High | Keep Informed | Mobile accessibility, simple interface, and reduced paperwork. | Low tech-literacy or perception that the app is a "monitoring/spying" tool. | Monthly Training Sessions & App Notifications (In-App).
Legal & Compliance Officer | Internal Auditor; ensures data privacy and legal standings. | High | Low | Keep Satisfied | Data security (GDPR/DPDP Act compliance) and audit-readiness for legal docs. | Legal hold if data privacy or security standards are not met. | Quarterly Compliance Review Meetings.
Parivahan / API Service Provider | External Data Source; provides the base vehicle information (Mocked for MVP). | High | Low | Keep Satisfied | API stability and security of the "Handshake" between systems. | API downtime or changes in the data schema/access rules. | Ad-hoc Technical Documentation Updates & Email Alerts.