## Sheet1
Req ID | Requirement Description | Source | User Story | Test Case ID | Implementation | Validation
FR-1.1 | Manual entry and validation of Indian Reg Numbers. | FSD Sec 4.1 | US-02 | TC-ONB-01 | Completed | Pass
FR-1.3 | Automated data fetch from Mock Vahan API. | FSD Sec 4.1 | US-02 | TC-ONB-02 | Completed | Pass
FR-2.1 | Calculate "Days to Expiry" for all documents. | FSD Sec 4.2 | US-03 | TC-LOG-01 | In Progress | Pending
FR-2.2 | Assign color status (Red/Yellow/Green) to rows. | FSD Sec 4.2 | US-03 | TC-LOG-02 | In Progress | Pending
FR-3.1 | Secure file upload for PDF, PNG, and JPG. | FSD Sec 4.3 | US-04 | TC-VLT-01 | Not Started | N/A
FR-4.1 | Automated WhatsApp simulation alerts. | FSD Sec 4.4 | US-05 | TC-ALT-01 | Not Started | N/A
FR-5.1 | Export compliance data to CSV format. | FSD Sec 7.4 | US-06 | TC-REP-01 | Not Started | N/A
NFR-1.4 | Input sanitization to prevent SQL Injection. | FSD Sec 8.1 | US-07 | TC-SEC-01 | Completed | Pass